## Plan
BATCH 159
Group: 1
Topic : Ryana Calendars Website
Team Members:
1. LE NGUYEN KHA ( Leader )
2. LE NGUYEN TOAN
3. VUONG HOANG LONG
IMPLEMENTATION PROCESS
WEBSITE INTERFACE AND FUNCTIONALITY | MEMBER | START | FINISH
Layout Ideas And Contents | All Members | 19/05/2020 | 26/05/2020
Design Logo | Vuong Hoang Long | 22/05/2020 | 24/05/2020
Project Plan | All Members | 26/05/2020 | 26/06/2020
Menu | Vuong Hoang Long | 26/05/2020 | 2020-01-06
Footers Website | Le Nguyen Toan | 26/05/2020 | 2020-03-06
Home Page | Le Nguyen Kha & V.H Long | 26/05/2020 | 2020-06-06
Page About | Le Nguyen Kha | 2020-07-06 | 15/06/2020
Search Products | Le Nguyen Toan | 2020-04-06 | 2020-10-06
Information Products | Vuong Hoang Long | 2020-02-06 | 2020-10-06
Products Suggestions | Vuong Hoang Long | 2020-10-06 | 15/6/2020
Page Location | Le Nguyen Toan | 14/06/2020 | 16/06/2020
Feedback | L.N Toan & V.H Long | 18/6/2020 | 23/06/2020
Login | Le Nguyen Kha | 16/6/2020 | 19/6/2020
Payment | Le Nguyen Toan | 2020-11-06 | 16/6/2020
BoxChat | Le Nguyen Toan | 18/6/2020 | 30/6/2020
Price List | Le Nguyen Kha | 19/6/2020 | 20/6/2020
Images For Website | Le Nguyen Kha | 27/5/2020 | 2020-09-07
Documents For Website | Le Nguyen Kha | 15/6/2020 | 2020-01-07
Code Completion | All Members | 30/6/2020 | 2020-01-07
SlideShow | Le Nguyen Kha | 2020-02-07 | 2020-09-07